## Start Here
PILARS · Bid/No-Bid Decision Workbook
Score the pursuit BEFORE the takeoff starts. A no-bid at that stage costs nothing.
HOW TO USE (5 minutes per pursuit)
| 1. | 1-Project — enter the project basics: value, duration, retention, pay terms, bidder count.
| 2. | 2-Calibration — enter YOUR shop's numbers: backlog, hit rate, estimating cost, margin, working capital.
| 3. | 3-Cash Exposure — the monthly AR model runs itself from steps 1-2. Check the peak AR and the suggested score.
| 4. | 4-Scorecard — answer the seven questions with the dropdowns. Model hints appear beside Q3 and Q7.
| 5. | 5-Verdict — read the decision, the red flags, and the levers that would flip it. Then act on it.
| 6. | 6-Pursuit Log — record every pursuit and its outcome. Your hit rate by score band builds itself.
CELL LEGEND
Orange-bordered white cells = YOUR INPUTS
Grey cells = calculated. Do not type over them.
DECISION BANDS (auto-calibrated to your backlog on 2-Calibration)
| BID |  | Score at or above the bid threshold. Pursue it and protect margin — do not buy the job.
| BID - LOADED MARKUP |  | Middle band, or AR between 20-40% of working capital. Bid with risk priced in.
| STRATEGIC ONLY |  | Lower band, or pay-history score of 0. Bid only for a key client or deliberate learning curve.
| NO-BID |  | Below the floor, or peak AR over 40% of working capital (hard kill). Decline within 48 hours.
HARD-KILL RULES (override the score — same engine as the web tool)
| · | Peak AR above 40% of working capital forces NO-BID regardless of score.
| · | Pay-history score of 0 (76+ days or open dispute) caps the verdict at STRATEGIC ONLY.
| · | Peak AR between 20-40% of working capital caps the verdict at BID - LOADED MARKUP.
Live web version with the same engine: pilars.ai/resources/bid-no-bid-scorecard · Method guide: pilars.ai/blog/bid-no-bid-scoring-model
Weights and decision bands follow FMI bid-hit-ratio research: 20-30% is the profitable zone for specialty subs, 10-15% for hard-bid GCs.

## 1-Project
1 · Project Brief
Identify the pursuit and enter its commercial shape. Orange-bordered cells are inputs.
IDENTIFICATION
| Project name | Sample - Medical Office Fit-Out | As it appears on the bid invitation.
| Owner | Regional Hospital System | The paying entity — pull pay history on THIS name.
| General contractor | Summit Builders | Leave blank if bidding direct to owner.
| Location | Dallas, TX | Market matters for labor and bidder depth.
| Trade / scope | Drywall & framing
| Bid due date | 2026-08-15 | The 48-hour no-bid letter clock starts at your decision.
| Estimator |  | Who owns this pursuit.
COMMERCIAL SHAPE
| Delivery method | Hard bid | Dropdown. Negotiated work justifies looser thresholds.
| Estimated contract value ($) | 2000000 | Your scope only, not project total.
| Duration on site (months) | 9 | Your billing window — drives the cash model.
| Retention (%) | 10% | As written in the bid documents.
| Pay terms (days) | 45 | Realistic days-to-pay, not the contract's promise.
| Known bidder count | 6 | From the plan-holder list. Feeds Q7's hint.

## 2-Calibration
2 · Shop Calibration
Your shop's economics tune the thresholds and the break-even math.
YOUR SHOP
| Current backlog (months) | 4 | 6+ months tightens the decision bands; under 2 loosens them.
| Current bid-hit rate (%) | 18% | Wins ÷ bids, trailing 12 months. Count withdrawn bids as losses.
| Estimating cost for this bid ($) | 4800 | Fully loaded hours: takeoff, quotes, RFIs, proposal.
| Expected gross margin on this job (%) | 12% | Realistic GP% for this scope if won at a defensible number.
| Available working capital ($) | 2000000 | Cash plus line of credit you can actually deploy.
CALCULATED
| Expected gross profit on this job |  | Contract value × expected margin.
| Break-even hit rate |  | Estimating cost ÷ gross profit per win. Your floor — below this, bidding loses money.
Hit rate vs break-even
DECISION THRESHOLDS (auto-calibrated to backlog)
| BID threshold |  | Standard 45/32/20. Full shop (6+ mo backlog): 50/38/25. Thin pipeline (≤2 mo): 40/28/17.
LOADED MARKUP threshold
STRATEGIC ONLY threshold

## 3-Cash Exposure
3 · Cash Exposure Model
Straight-line billing, lagged receipts, retention held. Where does AR peak — and can the balance sheet carry it?
Receipt lag (months)
Pay-terms days ÷ 30, rounded up.
Month | Billed | Cum billed | Received | Cum received | Outstanding AR | RESULTS
1 | [5 empty] | Peak outstanding AR
2 | [5 empty] | Peak AR ÷ working capital
3 | [5 empty] | Suggested Q3 score
4 | [5 empty] | Exposure zone
5
6 | [5 empty] | Assumes straight-line billing and no retention release inside the model window
7 | [5 empty] | (retention releases after the horizon — which is exactly when your cash is thinnest).
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24

## 4-Scorecard
4 · The Seven Questions
Pick an answer in every dropdown. Weights are fixed — 3x factors are where losing bids lose money.
Q# | Question | Your answer (dropdown) | Score | Weight | Weighted | Model hint
Q1 | Owner / GC pay history | 2 - Paid 46-60 days |  | 3
Q2 | Schedule fit vs. current backlog | 2 - Minor overlap, absorbable |  | 3
Q3 | AR exposure if it goes sideways | 1 - 20-40% of working capital |  | 3
Q4 | Key personnel (PM + foreman) | 2 - Both available, one stretched |  | 2
Q5 | Scope clarity & design maturity | 2 - CDs at 75-90% |  | 2
Q6 | Retention % and release triggers | 2 - 10% at substantial completion |  | 2
Q7 | Competitive field | 2 - 6-8 bidders |  | 1
| TOTAL WEIGHTED SCORE |  |  | of 63:
Score BEFORE the takeoff starts. Sunk-cost bias adds a point to every answer once hours are spent.

## 5-Verdict
5 · Verdict
The decision, the reasons, and what would change it.
SCORE
| Weighted score |  | BID at or above
| Points to a clean BID |  | LOADED MARKUP at
| Maximum possible | 63 | STRATEGIC at
PURSUIT ECONOMICS
Break-even hit rate
Your current hit rate
| Est. win probability (this job) |  | Your hit rate scaled by scorecard strength (clamped 2-60%).
| Expected value of bidding |  | Win% × gross profit − estimating cost. Negative = pursuit destroys money on average.
RED FLAGS
Peak AR exceeds 40% of working capital (hard kill)
Peak AR in the 20-40% caution zone
Pay history scored 0 (76+ days or dispute)
A 3x-weighted question at 1 or below
Shop hit rate below break-even
Negative expected value on this pursuit
IMPROVEMENT LEVERS — points available per question
| Question | Current | Points available
The longest bar is your cheapest path to the next band — renegotiate that term before you decline outright.

## 6-Pursuit Log
6 · Pursuit Log
Every pursuit, every outcome. After two quarters this table is worth more than any single bid.
| Bids submitted |  | Wins |  | Hit rate |  | GP won ($)
| Hit rate: score 45+ |  | 32-44 |  | 20-31 |  | Estimating $ spent
Band stats use the standard 45/32/20 bands. The curve should slope: highest hit rate in the top band.
Date | Project | Owner / GC | Trade | Score | Verdict | Result | Contract $ | Gross profit $ | Est. cost $

## Benchmarks
Hit-Ratio Benchmarks by Trade
Judge your log against your trade, not someone else's. Full guide: pilars.ai/blog/bid-hit-ratio-benchmarks-by-trade
| Trade / pipeline | Healthy range | Investigate below | Investigate above | Notes
| Electrical subcontractor | 20-30% | 10% | 40% | 4-6 bidder invitations typical
| Mechanical / HVAC subcontractor | 18-28% | 10% | 38% | Equipment quotes add spread
| Plumbing subcontractor | 20-30% | 10% | 40%
| Drywall / interiors subcontractor | 25-35% | 12% | 45% | Relationship-heavy packages
| Structural steel (fab & erect) | 15-25% | 8% | 35% | Capacity cycles swing pricing
| Concrete subcontractor | 20-30% | 10% | 40%
| Roofing (new construction) | 15-25% | 8% | 35% | Service work runs higher
| Sitework / earthwork | 15-25% | 8% | 35%
| GC - hard-bid public | 10-15% | 5% | 25% | 8-15 bidders, price only
| GC / sub - negotiated & CM-at-risk | 40-60% | 25% | - | Selection precedes pricing
Sources: FMI Contractor Business Performance Report; CFMA benchmarking. Count pursuits (not dollars), count withdrawn bids as losses,
and never blend negotiated with hard-bid pipelines. Above the 'investigate above' line usually means underpricing — check bid-tab spreads.
Template by PILARS — AI construction takeoffs at $100 per trade, per plan. pilars.ai

## Lists (hidden)
Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Delivery | Result | Verdict
3 - Paid 0-45 days, clean | 3 - Peak lands in a valley | 3 - Peak AR under 10% of working capital | 3 - PM & foreman both named and clean | 3 - CDs 95%+ with coordinated MEP | 3 - 5% released at substantial completion | 3 - 2-5 qualified invited bidders | Hard bid | Pending | BID
2 - Paid 46-60 days | 2 - Minor overlap, absorbable | 2 - 10-20% of working capital | 2 - Both available, one stretched | 2 - CDs at 75-90% | 2 - 10% at substantial completion | 2 - 6-8 bidders | Negotiated | Won | BID - LOADED MARKUP
1 - Paid 61-75 days / unknown owner | 1 - Peaks overlap within 30 days | 1 - 20-40% of working capital | 1 - One committed elsewhere | 1 - DDs with performance specs | 1 - 10% at final acceptance | 1 - 9-11 bidders | Design-build | Lost | STRATEGIC ONLY
0 - 76+ days or open dispute | 0 - Stacks on existing peak | 0 - Over 40% of working capital | 0 - Both committed to other projects | 0 - SD / design-build placeholder scope | 0 - Held through punch, no release trigger | 0 - 12+ open public bid | CM-at-risk | No-bid | NO-BID